## Sheet1
Bangabandhu Satellite - 2
Task Name | Start Time | End Time | Assignees
Prepare talking points for State Minister regarding the meeting with French Ambassador and Airbus EVP | 13/05/2024, 14:00 | 13/05/2024, 15:30 | [Touhidul Islam]
Prepare draft letter to French Ministry of Trade for state credit | 14/05/2024, 10:00 | 14/05/2024, 11:15 | [Touhidul Islam]
Review comparison between PwC report and Airbus proposal |  | 14/05/2024, 13:00 | [Touhidul Islam]
Revise the draft letter to French Ministry of Trade for state credit | 14/05/2024, 14:00 | 14/05/2024, 15:00 | [Touhidul Islam]
Print the comparison between PwC report and Airbus proposal | 14/05/2024, 15:00 | 14/05/2024, 15:15 | [Touhidul Islam]
Writeup on AIRBUS proposal for BS-2 | 15/05/2024, 11:30 | 15/05/2024, 12:30 | [Touhidul Islam]
Coordinate with Airbus to prepare the draft letter for BS-2 funding request | 15/05/2024, 14:00 | 15/05/2024, 16:00 | [Touhidul Islam]
Letter to Glavkosmos regarding invitation | 09/05/2024, 13:30 | 09/05/2024, 15:30 | [Touhidul Islam,Moue Islam]
Finalize letter for GLV as per Chairman's feedback | 09/05/2024, 17:30 | 09/05/2024, 18:30 | [Touhidul Islam]
ITU Related Activities
Task Name | Start Time | End Time | Assignees
BR-IFIC discs to be returned and new discs to be collected from BTRC | 15/05/2024, 11:00 | 15/05/2024, 12:00 | [Touhidul Islam,Moue Islam]
Other Technical Tasks
Task Name | Start Time | End Time | Assignees
Discussion on different solutions regarding smart presentation | 13/05/2024, 13:30 | 13/05/2024, 14:30 | [Touhidul Islam,sumaiya sabur]
NOCC - VSAT related activities in Gazipur | 15/05/2024, 09:30 | 15/05/2024, 13:00 | [Touhidul Islam]
Planning Administrative Tasks
Task Name | Start Time | End Time | Assignees
Preparatory meeting for 12 May program | 11/05/2024, 19:00 | 11/05/2024, 22:00 | [Muntasirur Rahman ,S M Anwarul Aziz,Touhidul Islam,sumaiya sabur]
Prepare correction for AV | 11/05/2024, 22:00 | 11/05/2024, 23:00 | [Touhidul Islam,S M Anwarul Aziz,sumaiya sabur]
Activities related to the AV for 12th May program | 12/05/2024, 09:00 | 12/05/2024, 11:00 | [Touhidul Islam,sumaiya sabur]
"à¦¨à¦¤à§à¦¨ à¦ªà§à¦°à¦•à¦²à§à¦ªà§‡à¦° à¦§à¦¾à¦°à¦¨à¦¾ à¦ªà¦¤à§à¦°" |  | 12/05/2024, 04:00 | [Touhidul Islam,S M Anwarul Aziz,Md Arafin Mahamud ]
Activities related to 12th May Program | 12/05/2024, 13:30 | 12/05/2024, 16:00 | [Touhidul Islam]
Prepare weekly activities report | 13/05/2024, 12:30 | 13/05/2024, 13:30 | [Touhidul Islam]
Prepare tender document for Procurement of Smart Presentation System | 13/05/2024, 15:00 | 13/05/2024, 16:00 | [Touhidul Islam,sumaiya sabur]
Discussion on Executive Asst. Recruitment |  | 14/05/2024, 10:30 | [Touhidul Islam]
Send photographs and reports to BSMMU | 14/05/2024, 10:00 | 14/05/2024, 11:00 | [Touhidul Islam,Moue Islam]
Pre-tender meeting on Basic Tools and 150 TRP Devices | 14/05/2024, 11:30 | 14/05/2024, 12:30 | [Touhidul Islam,S M Anwarul Aziz,Muntasirur Rahman ]
Mail to General Services for Video Conference solution |  | 14/05/2024, 14:30 | [Touhidul Islam,sumaiya sabur]
Legal consultant TOR report preparation | 14/05/2024, 15:15 | 14/05/2024, 16:00 | [Touhidul Islam]
Discussion on the way forward for procurement of Media log | 14/05/2024, 09:00 | 14/05/2024, 09:30 | [Touhidul Islam,S M Anwarul Aziz]
Discussion on Smart Presentation system and Innovation Contest |  | 14/05/2024, 09:30 | [Touhidul Islam,sumaiya sabur]
12 May BS-1 Launch Celebration Program: Video + Banner Preparation | 09/05/2024, 09:00 | 09/05/2024, 13:00 | [Touhidul Islam,sumaiya sabur]
12th May Program - Banner design | 09/05/2024, 13:30 | 09/05/2024, 16:00 | [Touhidul Islam]
Meeting with Chairman Sir on 12th May AV | 09/05/2024, 16:00 | 09/05/2024, 17:30 | [Touhidul Islam]
Television Rating Point (TRP)
Task Name | Start Time | End Time | Assignees
Physical Meeting with Nelco and Chairman sir | 12/05/2024, 11:00 | 12/05/2024, 13:00 | [Touhidul Islam,S M Anwarul Aziz,Md Arafin Mahamud ,Muntasirur Rahman ]
Assist to prepare letter & note about à¦°à¦¾à¦¶à¦¿à¦¯à¦¼à¦¾à¦¨ Roscosmos à¦à¦¬à¦‚ à¦œà¦¯à¦¼à§‡à¦¨à§à¦Ÿ à¦¸à§à¦Ÿà¦• à¦•à§‹à¦®à§à¦ªà¦¾à¦¨à¦¿ Glavkosmos à¦à¦° à¦¸à¦¾à¦¥à§‡ à¦•à¦¾à¦°à¦¿à¦—à¦°à¦¿ à¦“ à¦†à¦°à§à¦¥à¦¿à¦• à¦¬à¦¿à¦·à¦¯à¦¼à¦¾à¦¦à¦¿ à¦†à¦²à§‹à¦šà¦¨à¦¾ à¦à¦¬à¦‚ à¦¨à§‡à¦—à§‹à¦¸à¦¿à¦¯à¦¼à§‡à¦¶à¦¨ à¦à¦° à¦¬à¦¿à¦·à¦¯à¦¼à§‡ à¦ªà¦¤à§à¦° à¦ªà§à¦°à§‡à¦°à¦£ in D-nothi | 09/05/2024, 13:30 | 09/05/2024, 15:30 | [Moue Islam,Touhidul Islam]